## Sheet
Outstanding activities (weekly view)
ID | Week | Contract | ActivityIdentifier | Version | Shortnote | Planned startdate | Planned enddate | Name | Note
88 |  | Horizon 2020 - ODI | H2020-WP01-ACT-001 | 1.10 | D1.1b: Half-yearly ITEA2 progress reports |  |  | Abdelkrim BOUJRAF | Business requirement collector
88 |  | Horizon 2020 - ODI | H2020-WP01-ACT-001 | 1.10 | D1.1b: Half-yearly ITEA2 progress reports |  |  | Sven VD | Business writer
1088 | 2014-27 | Horizon 2020 - ODI | StratEx-WP01-ACT-001 | 1.10 | D1.1bb: Half-yearly ITEA2 progress reports | 01/07/2014 | 25/07/2014 | Abdelkrim BOUJRAF | Business requirement collector
1088 | 2014-27 | Horizon 2020 - ODI | StratEx-WP01-ACT-001 | 1.10 | D1.1bb: Half-yearly ITEA2 progress reports | 01/07/2014 | 25/07/2014 | Rudolf DS | Business writer
25 | 2014-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-ACT-002 | 1.00 | D1.1a: Half-yearly ITEA2 progress reports | 01/07/2014 | 31/12/2014 | Sven VD | Business writer
29 | 2014-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-RPT-001 | 1.00 | D1.3: Dissemination plan | 01/07/2014 | 31/12/2014 | Rudolf DS | Event organiser
29 | 2014-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-RPT-001 | 1.00 | D1.3: Dissemination plan | 01/07/2014 | 31/12/2014 | Rudolf DS | Event Orator
30 | 2014-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-RPT-002 | 1.00 | D1.4a: Market monitoring synthesis | 01/07/2014 | 30/06/2015 | Rudolf DS | Business writer
37 | 2014-40 | Horizon 2020 - ODI | H2020_StratEx_13047-WP02-RPT-001 | 1.00 | D2.1: Use cases definition | 01/10/2014 | 31/12/2014 | Rudolf DS | Business writer
38 | 2015-1 | Horizon 2020 - ODI | H2020_StratEx_13047-WP02-RPT-002 | 1.00 | D2.2a: Initial and updated requirements specifications | 01/01/2015 | 31/03/2015 | Rudolf DS | Technical Writer
26 | 2015-1 | Horizon 2020 - ODI | H2020-WP01-ACT-001 | 1.00 | D1.1b: Half-yearly ITEA2 progress reports | 01/01/2015 | 30/06/2015 | Rudolf DS | Business writer
27 | 2015-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-ACT-004 | 1.00 | D1.1c : Half-yearly ITEA2 progress reports | 01/07/2015 | 31/12/2015 | Rudolf DS | Business writer
31 | 2015-27 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-RPT-003 | 1.00 | D1.4b : Market monitoring synthesis | 01/07/2015 | 30/06/2016 | Rudolf DS
43 | 2015-27 | Horizon 2020 - ODI | H2020-WP04-ACT-001 | 1.00 | D4.1a: Proposition of secure patterns to deploy Identity Providers in cloud environments | 01/07/2015 | 30/09/2015 | Sven VD | Business writer
40 | 2015-40 | Horizon 2020 - ODI | H2020-WP02-RPT-001 | 1.00 | D2.2b: Initial and updated requirements specifications | 01/10/2015 | 31/12/2015 | Sven VD | Technical Writer
49 | 2015-40 | Horizon 2020 - ODI | H2020-WP06-ACT-002 | 1.00 | D6.2a: Demonstrators specifications | 01/10/2015 | 31/12/2015 | Sven VD | Technical coordinator
52 | 2015-40 | Horizon 2020 - ODI | H2020-WP06-ACT-005 | 1.00 | D6.3a: Demonstrators specifications | 01/10/2015 | 31/12/2015 | Sven VD | Technical coordinator
55 | 2015-40 | Horizon 2020 - ODI | H2020-WP06-ACT-008 | 1.00 | D6.4a: Demonstrators specifications | 01/10/2015 | 31/12/2015 | Sven VD | Technical coordinator
28 | 2016-1 | Horizon 2020 - ODI | H2020_StratEx_13047-WP01-ACT-005 | 1.00 | D1.1d : Half-yearly ITEA2 progress reports | 01/01/2016 | 30/06/2016 | Sven VD | Business writer
45 | 2016-14 | Horizon 2020 - ODI | H2020-WP04-ACT-003 | 1.00 | D4.3b, software: Adequate authentication software applications | 01/04/2016 | 31/05/2016 | Sven VD | Business writer
47 | 2016-14 | Horizon 2020 - ODI | H2020-WP05-ACT-002 | 1.00 | D5.2b, software: End-to-end privacy assurance software modules | 01/04/2016 | 30/06/2016 | Sven VD
53 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-006 | 1.00 | D6.3b software: Demonstrators | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator
54 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-007 | 1.00 | D6.3c: Evaluation report | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator
50 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-003 | 1.00 | D6.2b software: Demonstrators | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator
51 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-004 | 1.00 | D6.2c: Evaluation report | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator
56 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-009 | 1.00 | D6.4b software: Demonstrators | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator
57 | 2016-40 | Horizon 2020 - ODI | H2020-WP06-ACT-010 | 1.00 | D6.4c: Evaluation report | 01/10/2016 | 31/12/2016 | Marc V. | Technical coordinator